## Sheet1
Risk ID | Recommendation | Owner | Target Date | Status
R001 | Implement MFA and phishing awareness training | IT Manager | 30 Days | Open
R002 | Introduce RBAC and quarterly access reviews | IT Manager | 60 Days | Open
R003 | Deploy EDR and conduct backup testing | IT Manager | 60 Days | Open
R004 | Create disaster recovery plan and test annually | IT Manager | 90 Days | Open
R005 | Introduce supplier security assessments | HR Manager | 90 Days | Open
R006 | Conduct quarterly backup restoration tests | IT Manager | 30 Days | Open
R007 | Implement logging and periodic access reviews | Operations Manager | 60 Days | Open
R008 | Enforce MFA and stronger password requirements | IT Manager | 30 Days | Open
R009 | Enable BitLocker encryption and remote wipe capability | IT Manager | 30 Days | Open
R010 | Conduct GDPR review and staff training | Compliance Officer | 60 Days | Open
R011 | Restrict repository access and enforce MFA | Development Manager | 30 Days | Open
R012 | Perform CRM security review and access audit | Sales Manager | 60 Days | Open
R013 | Establish formal policy review schedule | Compliance Officer | 90 Days | Open
R014 | Review support platform permissions and logging | Operations Manager | 60 Days | Open
R015 | Conduct HR access review and monitoring | HR Manager | 60 Days | Open